# INVITATION TO BID
DESIGN-BUILD CONSTRUCTION PROJECT ISSUED May 24, 2022

CATAWBA ISLAND TOWNSHIP
WEST HARBOR BOAT LAUNCH IMPROVEMENTS

The Catawba Island Township Trustees will accept sealed bids for this project until 6:00pm June 28, 2022 at the Administration Building located at 4822 E Cemetery Road, Port Clinton, OH 43452, at which time the bids will be read aloud.

If a bid is mailed it is required to be placed within another sealed envelope marked, “West Harbor Launch Sealed Bid.”

A pre-bid meeting will be held June 7, 2022 at 1:00pm at the Administration building to answer questions about the project by potential bidders.

Table of Contents

  1. PROJECT INTRODUCTION	3
  2. SCOPE	3
  3. LOCATION	3
  4. DESCRIPTION	3
  5. SCHEDULE	3
  6. INFORMATION	3
  7. DATA AND MATERIALS TO BE PROVIDED BY CATAWBA ISLAND TWP.	4
  1. PROJECT REQUIREMENTS	5
  2. GENERAL REQUIREMENTS	5
    1. SCOPE OF WORK AND PROJECT SUMMARY/REQUIREMENTS	5
    2. PROGRESS PAYMENTS	5
    3. PROJECT MEETINGS	5
  3. DESIGN REQUIREMENTS	6
    1. DB DESIGN DEVELOPMENT AND CONSTRUCTION DOCUMENTS	7
  4. CONSTRUCTION REQUIREMENTS	7
    1. ENVIRONMENTAL AND SUSTAINABILITY REQUIREMENTS FOR CONSTRUCTION	7
    2. CONSTRUCTION SUPPORT	8
    3. WORKING HOUR RESTRICTIONS	8
    4. ACCESS	8
    5. PROJECT CLOSE-OUT	8
    6. SUBSTANTIAL COMPLETION AND FINAL INSPECTION	9
    7. PREVAILING WAGE	9
3.0 ATTACHMENT	10

  1. PROJECT INTRODUCTION

Project Name: West Harbor Boat Launch Improvement Project

  1. Scope

In accordance with the terms and conditions of the Contract, the Design-Build Contractor (DBC) shall perform the work of this Project for Catawba Island Township Trustees as described below.

The work of this Project shall be performed in accordance with the Ohio Building Code, enforced by the Ottawa County Building Inspection Department.

The DBC Team is responsible for providing all design and construction services required for the project inclusive of, but not limited to, the following: architectural, electrical, structural, mechanical, and any other required specialty.

  1. Location

This project is located 1955 NE Catawba Road, Port Clinton, Ohio.

  1. Description

Projects is for design and build improvements to the existing boat launch facilities including an ADA accessible restroom and dock along with site and lighting improvements.

  1. Schedule

The work in this Project shall be completed in accordance with the following schedule: DB Design Development Documents:
DB Design Development Documents submitted no later than 30 calendar days after award date of June 28, 2022.

Catawba Island Township review completed no later than 30 calendar days after submission of DB Design Development Documents.

100% Draft DB Construction Documents:

Work on Construction Documents shall continue during the Design Development Documents review and once Design Development review comments are received, they shall be addressed and incorporated in the Construction Documents.

Complete Stamped and Signed DB Construction Documents:

Complete Stamped and Signed DB Construction Documents to Catawba Island Township Trustees and Ottawa County Building Inspection no later than 7 calendar days after receipt 100% Draft DB Construction Document review comments.

Construction:

Construction completed no later than 120 calendar days after award of the contract.

As-Constructed Drawings:

As-Constructed Drawings completed no later than 30 calendar days after Project Completion.

All DB Design Development, DB Construction Documents and As-Constructed Drawings shall be submitted to Catawba Island Township Trustees.

  1. Information

Catawba Island Point of Contact:

#### Contractual & Technical:
Owner Representative (OR):
William Rofkar, Township Trustee WRofkar@catawbaislandtownship.com
  419-797-4131 (o) 419-341-6413 (c)

Address:
4822 E. Cemetery Rd
Port Clinton, OH 43452

  1. Data and Materials to be provided by Catawba Island Township
The following data will be provided to the DBC and are included in Section 3 of this RFP: Aerial photos of existing site depicting approximation of work to be completed.

  1. PROJECT
  1. General Requirements

    1. Scope of Work and Project Summary/Requirements

The project will consist of the design and construction of an ADA compliant year round restroom facility and various site improvements which will include but are not limited to the following:

- Demolition and disposal of existing restroom building and slab, back-fill disturbed area with appropriate fill material including a minimum of 12 inches of clean topsoil, seed and mulch disturbed area
- Design and construction of new, year round ADA compliant restroom facility including a storage/utility room with sink and a hose faucet approximately 450 sq ft in size.
- Approximate location of new restroom facility to be 400’ west of existing restroom building. Building to be designed using electric heat, without air conditioning.
- Lighting improvements on site including burial of overhead lines and updating existing fixtures with LED lighting (see attached map)
- Cleaning and painting exiting light poles with appropriate black paint
- Installation of an ADA dock system to be attached to the existing northern most launch slip
- Replace existing floating docks

Design Build Contractor will be responsible for at a minimum, the following and other pertinent information as the project calls for:

      1. Review site data.
      2. Upon award, determine and provide design schedule of work
      3. Obtaining all required permits
      4. Submit DB Design Development and DB Construction Documents for review and approval, as required
      5. Provide schedule of construction work
      6. Secure work area and provide for continued access to the facility
      7. Construct project
      8. Provide as-constructed drawings

    1. Progress Payments

Design Phase - Progress payments during the design phase of the work will be based on submission, review, and acceptance of design deliverables.

Construction Phase - Progress payments during construction will be based on the percentage of work completed on items listed on the approved schedule of values. Actual construction completed and in place will form the basis for payment.

    1. Project Meetings
#### Pre-bid Meeting
A pre bid meeting will be June 7, 2022 at 1 pm at the Catawba Island Township administration building, 4822 Cemetery Road, Port Clinton to the to review the scope of the project and for the contracting authority to answer any questions potential bidders have in regards to the project.

#### Design Meeting
After the award of the contract and acceptance of the required insurance and bonds, the OR will arrange a design meeting with the DBC. The meeting agenda shall include the following as a minimum:

      1. Review and emphasize the needs and design objectives of the project
      2. Design schedule (provide minimum of two hard copies and one electronic). Note: No portion of the work can begin construction until 100% Complete DB Construction Documents are approved.
      3. Modifications during design
      4. Submittals during design
      5. Areas available for use by the DBC
      6. Payments to the DBC

#### Preconstruction Meeting

After 100% Complete DB Construction Documents are approved and prior to the start of construction, the OR will arrange an on-site Preconstruction meeting with the DBC. The meeting agenda will include the following as a minimum:

      1. Designation of your Project Superintendent
      2. Project Schedule with construction portion fully developed
      3. A list of subcontractors for this project
      4. Waste Management Plan
      5. Quality Control Plan
      6. Correspondence procedures
      7. Roles and responsibilities
      8. Progress Payments
      9. Submittal process
      10. Construction schedule (provide a minimum of two color hard copies and electronic copy in software it was created in) Note: No portion of the construction can begin until 100% Complete DB Construction Documents are approved.
      11. Work days (Saturdays, Sundays, holidays and night work etc)

  1. Design Requirements

    1. DB Design Development and Construction Documents

This element of work shall consist of the preparation of the DB Design Development Documents and DB Construction Documents.

#### DB Design Development
DB Design Development Documents:

Submit 2 paper copies and one electronic copy of the Draft DB Design Development Documents for review.

#### DB Construction Documents
100% Draft DB Construction Documents

  - Submit 2 paper copies and one electronic copy of the 100% Draft DB Construction Documents for review.

Complete Stamped and Signed DB Construction Documents

  - Submit 2 paper copies and one electronic copy of the 100% Completed Stamped and Signed DB Construction Document.
  - Submit appropriate set of construction drawings to Ottawa County Building Inspection to obtain proper permits

  1. Construction Requirements

    1. Environmental and Sustainability Requirements

      1. Air: Employ construction practices that minimize dust production and combustion byproducts.

      1. Noise: Minimize noise generation during construction. Operate power equipment in accordance with local noise restrictions.

      1. Waste Management Goals: Employ processes that ensure the generation of as little waste as possible. Waste disposal in landfills shall be minimized.

      1. All material unsuitable for recycling must be disposed of, in a legal manner.

    1. Construction Support Staging Areas
Construction site will be limited to the smallest feasible area.

Staging is limited in or near the construction area for a construction trailer. Construction equipment and material storage shall be located in areas near the construction site. All staging areas shall be returned to pre-construction conditions once construction is complete.

Structures:
Trailers, Storage, Staging Area: Location to be approved by the Contracting Officer.

#### Parking of Construction Vehicles

Parking of vehicles shall be limited to existing parking area, and within approved staging area(s).

    1. Working Hour Restrictions

All work shall be limited to the weekday hours of 7:00 a.m. to 6:00 p.m., unless otherwise approved by the OR.

    1. Access

Coordinate construction efforts with the OR such that there is minimal impact to the visiting public.

    1. Project Close-out

Project Record Drawings: Maintain one complete full-size set of contract drawings and one
full-size set of vendor-supplied drawings. Clearly mark changes, deletions, and additions to show actual constructed conditions. Keep record drawings current. Certification of accuracy and completeness will be required for payment requisitions. On completion of the total project, submit complete record drawings.

As-Constructed Drawings: Provide as-constructed drawings by updating the Approved DB Construction Drawing with information provided on the record drawings, contract modifications; and other applicable shop drawings, sketches, and data.

Provide as-constructed drawings in the following formats:
      1. 1 electronic copy in PDF
      2. 2 full-size paper copies

Before submitting a request for final inspection, submit the following:
      1. Project Record Drawings and As-Constructed Drawings: As specified above.
      2. Guarantees and Bonds: As specified in Performance Requirements and Specifications.
      3. Mechanical and Electrical Systems: Verify the following in writing:
        1. All systems are complete.
        2. All systems have been properly started and are operational.
        3. All controls are complete and operational, and sequences have been checked and are functioning properly.
    2. Substantial Completion and Final Inspection

Submit written certification that project, is substantially complete, and request in writing a final inspection. Upon receipt of written request that project is substantially complete, the OR will proceed with inspection within 5 days of receipt of request or will advise the Contractor of items that prevent the project from being designated as substantially complete.

When work is determined to be substantially complete, the OR will prepare a list of deficiencies ("Punch List") to be corrected before final acceptance. The OR will issue a Letter of Substantial Completion. If work is not determined to be substantially complete, the OR will notify the DBC in writing. After completing work, the DBC shall resubmit certification and request a new final inspection.

If, following final inspection, the work is determined to be substantially complete, Contracting Officer will prepare a list of deficiencies to be corrected before final acceptance and issue a Letter of Substantial Completion. Contractor shall complete the work described on the list of deficiencies within 10 calendar days. If the Contractor fails to complete the work within this time frame, the OR may either replace or correct the work with an appropriate reduction in the contract price or charge for re-inspection costs.

Acceptance of the work: After all deficiencies have been corrected, the Contracting Officer will issue a Letter of Acceptance.

2.3.7 Prevailing Wage Rates

This project is being funded with Ohio Department of Natural Resources (ODNR) grant dollars. The successful Bidder is responsible under the terms of the Contract to pay prevailing wages as found in the State of Ohio Prevailing Wage Determinations, and to all EEO requirements. Any Contractor or Subcontractor engaged in the performance of the project shall submit personnel and payroll information to that Public Authority's prevailing wage coordinator during the life of the Contract. Bidders are responsible for verifying that the most current wage rates are being utilized in their bids. The Contractor is also responsible for any changes in the prevailing wage rates or classifications throughout its performance of work on the project.

The Contractor shall comply with U.S. Department of Labor Regulations, Title 29, Subtitle A, Part 5, Sections 5.5, 5.31 and 5.32. In addition, The Contractor shall be responsible for submitting to the Contracting Authority its required payroll reports.

The Contractor shall be responsible for assuring that all its subcontractors comply with prevailing wage requirements and that all subcontractors provide the Contracting Authority with the required payroll reports.

The Contractor hereby acknowledges that it is responsible for the compliance itself and of any and all subcontractors with State of Ohio Prevailing Wage and its laws, and that lack of compliance with any requirements of prevailing wage laws by it or any Subcontractor shall give the Contracting Authority the right to withhold payments under this Contract until such requirements are met.

A schedule of the most current prevailing wage rates may be accessed by registering with the Ohio Department of Commerce, Labor and Worker Safety Division, Wage and Hour Bureau at the following web address:

http://198.234.41.198/w3/webwh.nsf?Opendatabase

The Contractor and all subcontractors shall compensate the employees on this contract at a pay rate not less than the hourly wage and fringe rate listed on the website noted above, for the applicable job classification or as may be modified by the Ohio Department of Commerce, Division of Labor and Worker Safety Wage and Hour Bureau, when new prevailing rates are established.

Overtime shall be paid at one and one-half times the basic hourly rate for any hours worked beyond forty hours during a pay week.  The Contractor and all subcontractors shall pay all compensation by company check to the worker and fringe benefit program.

The wage and fringe rates determined for this project or as may be later modified, shall be posted by the Contractor in a prominent and accessible place on the project, field office, or equipment yard where they can be easily read by the workers or otherwise made available to the workers.  On the first pay date of contract work the Contractor and all subcontractors shall furnish each employee covered by prevailing wage a completed form whpw1512 in accordance with section 4115.05 of the Ohio Revised Code, showing the classification, hourly pay rate, fringes, and identifying the Prevailing Wage Coordinator (PWC), if such employees are not covered by a collective bargaining agreement or understanding between employers and bona fide organizations of labor.  These forms shall be signed by the Contractor or subcontractor and the employee and kept in the Contractor’s or subcontractor’s payroll files.

## 3.0 ATTACHMENTS
Aerial photos of existing site depicting approximation of work to be completed (contractor responsible for visiting site to verify conditions and locations etc.)